## timeline
ID | content | start | end | group | owner
1 | Draft budget | 2018-08-06 | 2018-08-11 | 1 | LK
1 | Second draft of budget | 2018-08-27 | 2018-09-01 | 1 | LK
2 | Draft budget justification | 2018-08-27 | 2018-09-01 | 1 | LK
2 | Review budget justification | 2018-09-04 | 2018-09-08 | 1 | LK
2 | Second draft of budget justification | 2018-09-04 | 2018-09-08 | 1 | LK
3 | Rough draft of all portal text fields | 2018-08-06 | 2018-08-11 | 1 | LK
3 | Review and edit portal text fields | 2018-08-13 | 2018-08-18 | 1 | JA
3 | Review and edit portal text fields | 2018-09-04 | 2018-09-08 | 1 | LK
3 | Final review and edit of portal text fields | 2018-09-04 | 2018-09-08 | 1 | KD
4 | Decide on five key personnel to include | 2018-08-13 | 2018-08-18 | 1 | KD
4 | Edits / updates to all biosketches | 2018-08-20 | 2018-08-25 | 1 | JA
4 | Send draft biosketches to all key personnel | 2018-08-27 |  | 1 | JA
4 | Edits due from all on biosketches | 2018-09-17 |  | 1 | All
5 | Move Board of Directors to folder | 2018-08-06 |  | 2 | LK
5 | Confirm Board of Directors list is up to date | 2018-08-27 | 2018-09-01 | 2 | LK
6 | First draft of project workplan | 2018-08-13 | 2018-08-25 | 2 | KD
6 | Edit and review project workplan (send to ECANA SG and SGO) | 2018-08-27 | 2018-09-01 | 2 | JA, LK
6 | First draft of project timeline | 2018-08-27 | 2018-09-01 | 2 | LK
6 | Review and edit project timeline | 2018-09-04 | 2018-09-08 | 2 | JA
6 | Edits due from all on first draft of project workplan | 2018-09-07 |  | 2 | SG
6 | Second draft of project workplan | 2018-09-10 | 2018-09-14 | 2 | KD
6 | Final review and edit of project timeline | 2018-09-17 | 2018-09-21 | 2 | KD
6 | Final review and edits to project workplan | 2018-09-17 | 2018-09-21 | 2 | Trio
6 | Discuss nearly final project workplan at Sept. SG meeting | 2018-09-19 |  | 2 | Trio + SG
7 | Rough draft of milestones and deliverables | 2018-08-27 | 2018-09-01 | 1 | LK
7 | Review and edit milestones and deliverables | 2018-09-04 | 2018-09-08 | 1 | JA
7 | Second draft of milestones and deliverables | 2018-09-10 | 2018-09-14 | 1 | LK
7 | Final review and edit of milestones and deliverables | 2018-09-17 | 2018-09-21 | 1 | KD
8 | Draft LOS for existing partners | 2018-08-20 | 2018-08-25 | 2 | JA
8 | Send LOS to existing partners for edits | 2018-08-27 |  | 2 | JA
8 | Draft LOS for new partners | 2018-08-27 | 2018-09-01 | 2 | JA
8 | Send LOS to new partners for edits | 2018-09-04 |  | 2 | KD
8 | Signed LOS due from all partners | 2018-09-17 |  | 2 | All
10 | Business documents due to ABC | 2018-09-12 |  | 1 | LK
10 | Science documents due to ABC | 2018-09-24 |  | 2 | LK

## components
Group | Item (parent folder) | Status
Business | 1. Budget | Draft started in folder
Business | 2. Budget justification | Not started; original ECANA copied over, can use some language
Business | 3. Organization and Project Lead Info (Portal text folder) | Draft copied over from original ECANA proposal; needs review from KD / JA
Business | 3. Project Information (Portal text folder) | Draft copied over from original ECANA proposal; needs review from KD / JA
Business | 3. Project Summary (Portal text folder) | Draft copied over from original ECANA proposal; needs review from KD / JA
Science | 4. Biosketches for all Key Personnel (limit of 5) | Biosketches from ECANA and ITHS copied into folder
Science | 3. Collaboration and Partnerships (Portal text folder) | Draft copied over from original ECANA proposal; needs review from KD / JA
Science | 5. Board of Directors List | ECANA BoD saved in folder
Science | 6. Project Workplan and Timeline
Science | 7. Project Deliverables / Milestones
Science | 8. Letter of Support - Bridgette | Drafts from ECANA and ITHS saved in folder
Science | 8. Letter of Support - SGO | Draft from ECANA saved in folder
Science | 9. Recent Articles / Evaluations

## priorities
Fortnight | Person | Item
8/13 - 8/24/18 | JA | Review portal text document + make initial edits
8/13 - 8/24/18 | JA | Draft LOS for existing partners + send out for edits
8/13 - 8/24/18 | KD | Decide on key personnel to include
8/13 - 8/24/18 | KD | Email SGO re: grant + LOS
8/13 - 8/24/18 | KD | Draft workplan
8/13 - 8/24/18 | KD | Work on identifying new partners + initial outreach
8/13 - 8/24/18 | LK | Out of office
8/27 - 9/7/2018 | JA | Draft biosketches + send to key personnel
8/27 - 9/7/2018 | JA | Draft LOS for new partners
8/27 - 9/7/2018 | KD | Out of office (8/27 - 8/31)
8/27 - 9/7/2018 | KD | Send LOS to new partners for edits
8/27 - 9/7/2018 | LK | Draft budget justification
8/27 - 9/7/2018 | LK | Review + edit portal text document
8/27 - 9/7/2018 | LK | Budget edits
9/10 - 9/24/2018 | JA | Double check budget against justification
9/10 - 9/24/2018 | KD | Review LOS for new partners + send out for edits
9/10 - 9/24/2018 | KD | Final review and approval of portal text documents
9/10 - 9/24/2018 | KD | Final review and approval of business documents
9/10 - 9/24/2018 | LK | Update portal text document
9/10 - 9/24/2018 | LK | Submit final business and draft science to ABC
9/10 - 9/24/2018 | LK | Submit final science to ABC
9/10 - 9/24/2018 | Trio | Final review and proofread of science components
9/10 - 9/24/2018 | Trio | Final review and proofread of business components